## Sheet1
Priority | Product Backlog Item | User Story # | Total Hours
1 | AR Indoor Navigation System | 4,6,7,8,9,13,16
| Designing of the Map |  | 2
| Designing the targets |  | 1
| Adding the necessary features |  | 1
| Coding for the AR Navigation System |  | 10
| Coding for the QrCode Scaning System |  | 5
2 | Login System | 1,18
| Designing of the Login Page |  | 1
| Designing of the SignUp Page |  | 1
| Designing the Error/Notification Messages |  | 1.5
| Designing Forget Password Page |  | 1
| Coding For the login System |  | 10
| Setting Up Firebase Authentification |  | 5
3 | Welcome Screens and Other screens | 2,3,5,11
| Designig Welcome Screen |  | 1
| Designing a Screen to Select Floor Buttons |  | 2
| Coding these screens for necessary buttons |  | 4